## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | STT041b SWN_RIVER IRWELL_ROCH | Author | [✂] (UU Environmental Planner, PLE)
Date: | 26/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | Manchester City Council Bury Metropolitan Borough Council Bolton Metropolitan Borough Council
Planning permission | Yes
Environmental Impact Assessment (EIA) | Screening Required - High Risk
Abstraction Licence | Yes
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 3 | An Enviornmental Impact Assessment (EIA) is likely to be required to support the Planning Application.This will add significant time and cost onto the programme. The area identified [✂] would be subject to significant scrunity by the LPA and key stakeholders due to it's location within an area of Green belt and adjacent to Heaton Park. Heaton Park is a heavily used recreational park and a Registered Park and Garden designated by Historic England. It is recommended to consider other sites further away from Heaton Park and a thorough site selection exercise would be required to support any planning application. Available sites could be in either Bury MBC or Manchester CC areas. A new abstraction licence will be require which has a lead time of approximately 2 years. Early consultation will be required with the relevent stakeholders to determine the exact location of the abstraction point.
1
2
3
Note on A13: 3 (HIGH) = Significant PLE constraints with long lead in time, which have potential to conflict with project output date, eg highly sensitive scheme, with complex consenting requirements and extensive stakeholder engagement, advance surveys or consents required and/or advanced site preparation required within outside of specific season.Significant likelihood of conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents will be extremely challenging to obtain. To enable successful delivery of the project there will be a need for multiple/complex activities including stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is significant potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 2 (MEDIUM) = Significant PLE constraints which can be managed within the proposed project output date. Lead in times still required for ecology, landscape and planning requirements. Applicable agreements, permissions or regulatory consents may be challenging to obtain. To enable successful delivery of the project there will be a need for activities which may include stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 1 (LOW) = PLE issues identified but which can be managed through specialist resource and BAU processes within proposed output date. Some limited potential for conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents are likely to be necessary but straightforward. There is low potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals.

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Landscape Designation: The area identified for the new [✂] is located within an area of Greenbelt. Visual Impact will be a prime concern. Statutory Wildlife Designation: N/A Local Level Wildlife Designation: Heaton Park Reservoir and Bridle Wood & Pond are both Sites of Biological Importance which are located adjacent to the proposed land purchase area. Historic England Designation: Heaton Park Registered Park & Garden is loacted adjacent to the proposed [✂] location. Planning Policy Designation: Greenbelt, Leisure Improvement Area, Minerals and Waste | Refer to Constraints tab and Environmental Review Plan
2 | Trees & Hedgerows | Yes | There are trees and hedgerows within and along the boundary of the proposed area for land purchase, in particular the land to the south which includes a woodland area. There will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
3 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Yes | Heaton Park is a designated Historic Park and Garden by Historic England and heavily used for recreational purposes. Impacts to amenity spaces should be avoided where possible.
4 | Access land - Village Green, Common Land, Millennium Greens etc. | Potentially | Dependent of final routeings but none identified currently.
5 | Heritage and Archaeology | Yes | An archaelogical desk based assessment will be required with possible further investigations and mitigation measures. Heaton Park Reservoir Pumping Station is a Grade II Listed Building. Any works to this building or within it's curtilage will require Listed Building Consent from the Local Authority
6 | Tree Preservation Order | Potentially | Dependent of final routeings - tbc
7 | Public Right of Way | Yes | There are Public Rights of Way (PRoW) within the vicinity of the land purchase area and pipeline routes. A PRoW closure will be required if these are to be diverted or closed during the construction phase.
8 | Main Rivers | Yes | The River Irwell and the River Roch are both designated as main rivers. A Flood Risk Activity Permit will be required from the Environment Agency for any works within 8m unless exempt. A Flood Risk Assessment and Geomorphological Assessment will be required to support the applications. Early consultation with the Environment Agency and Natural England will be required.
9 | Ordinary Watercourses | Yes | Both pipeline routes cross a number of ordinary watercourses. Any works which impact on these and where existing crossing points or no dig techniques can't be used will need approval from the Lead Local Flood Authority.
10 | Flood Risk Zone | Yes | Both pipeline routes cross Flood Risk Zone 2 and 3. The land purchase area is within Flood Risk Zone 1. In the event that a Planning Application is required any works outside of Flood Zone 1 a will require a Flood Risk Assessment to accompany the Planning Application.
11 | EIA Screening Opinion | Yes | The development proposals exceeds the thresholds set out in Schedule 2 of the Town and Country Planning (Environmental Impact Assessment) Regulations 2017 and as such an EIA Screening Opinion would need to be submitted to Manchester CC, Bolton MBC and Bury MBC.
12 | Environmental Impact Assessment | Potentially | It is likely that an Environmental Impact Assessment will be required to support the Planning Application. This will add significant time and cost onto the programme.
13 | Planning Permission | Yes | Planning Permission will be required for all above ground development required in connection with the construction of the new WTW and abstraction infrastructure. Permitted development rights will in effect be removed if the development requires EIA.
14 | Discharge Permit | Yes | Any new discharge permits should be confirmed with the Environment Agency.
15 | Abstraction Licence | Yes | The new abstraction will require an Abstraction Licence which should be should be confirmed with and obtained from the Environment Agency.
Yes
No
Potentially

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Constraints
Land Purchase Area | Local Plan
| Manchester City Council | Bury Council
EA Flood Risk Map | Tree Preservation Order Check
Public Rights of Way
Historic England Register