## Sheet1
Site Name | UU AMP8 Project ID | Unique WINEP ID | Primary regulatory EA driver | Primary driver description | WINEP Completion Date | Current UU planned completion date (July 2026 data) | Expected modelled spill-reduction outcome (per annum)
Hawkshead PS | U.80065577 | 08UU101164a | EnvAct_IMP2 | Improvements to reduce storm overflows spills to protect the environment so that they have no local adverse ecological impact. | 2030-03-31 | 2029-10-08 | 98
Near Sawrey WwTW | U.80065605 | 08UU101171a | EnvAct_IMP2 | Improvements to reduce storm overflows spills to protect the environment so that they have no local adverse ecological impact. | 2030-03-31 | 2027-09-30 | 72
Near Sawrey WwTW | U.80066975 | 08UU102493a | WFD_ND | Water Framework Directive actions to meet requirements to prevent deterioration | 2030-03-31 | 2028-03-28 | Not applicable
Ambleside WwTW | U.80066978 | 08UU102482a | 25YEP_IMP | Locally significant environmental measures not eligible under any other driver, but with clear evidence of customer support | 2030-03-31 | 2027-05-27 | Not applicable
Ambleside WwTW | U.80065509 | 08UU101136a | EnvAct_IMP4 | Improvements to reduce storm overflows spills so that they do not discharge above an average of 10 rainfall events per year by 2050. | 2030-03-31 | 2027-12-24 | 28.9
Elterwater PS | U.80065557 | 08UU101197a | EnvAct_IMP2 | Improvements to reduce storm overflows spills to protect the environment so that they have no local adverse ecological impact. | 2030-03-31 | 2026-09-30 | 21
Grasmere WwTW | U.80066976 | 08UU102480a | 25YEP_IMP | Locally significant environmental measures not eligible under any other driver, but with clear evidence of customer support | 2030-03-31 | 2026-08-26 | Not applicable
Grasmere WwTW | U.80066982 | 09UU102492a | EnvAct_IMP4 | Improvements to reduce storm overflows spills so that they do not discharge above an average of 10 rainfall events per year by 2050. | AMP9 (2030 to 2035) | 2030-03-29 | Not applicable
Glebe Road PS | U.80066980 | 08UU102491a | EnvAct_IMP3 | Improvements to reduce storm overflows that spill to designated bathing waters to protect public health. | AMP9 (2030 to 2035) | 2029-12-13 | 3.3