## Cover Sheet
Environmental Desk Based Assessment - Section 1
Project Name: | WR102B GWE_WIDNES | Author | [✂] (UU Environmental Planner, PLE)
Date: | 10/05/2022 | Reviewer | [✂] (UU Head of PLE)
Project Summary:
Local Authority(ies) | Liverpool City Council Knowsley Council
Planning permission | Yes
Environmental Impact Assessment (EIA) | Screening opinion required - moderate risk
Abstraction Licence | Existing Abstraction - increase abstraction within LicQ
Risk Rating (1 low, 2 medium, 3 high) |  | Summary/Recommendations
Risk Rating | 3 | Netherley: - Planning permission and EIA screening required. - The proposed area for development [✂] is an open area of amenty greenspace located within a residential area and adjacent to a Sports Club. Likely to be heavily used by local community. - Located within an area of designated Greenbelt. - Historic issues [✂] due to tree removal and visual impact. - Stakeholder engagement required to determine the solution Greensbridge: - Planning permission and EIA screening required. - Located within an area of designated Greenbelt. - Located within Flood Risk Zone 2 and 3. Engagement regarding the siting and design required with the EA. A flood risk assessment would be required to accompany the planning application. Potential need to relocate from the flood zone. Belle Vale: - Planning permission would be required for any new buildings including large kiosks or accesses off a classifed road. Potentially all 3 sites need to be considered together for the purposes of the EIA regulations
1
2
3
Note on A13: 3 (HIGH) = Significant PLE constraints with long lead in time, which have potential to conflict with project output date, eg highly sensitive scheme, with complex consenting requirements and extensive stakeholder engagement, advance surveys or consents required and/or advanced site preparation required within outside of specific season.Significant likelihood of conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents will be extremely challenging to obtain. To enable successful delivery of the project there will be a need for multiple/complex activities including stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is significant potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 2 (MEDIUM) = Significant PLE constraints which can be managed within the proposed project output date. Lead in times still required for ecology, landscape and planning requirements. Applicable agreements, permissions or regulatory consents may be challenging to obtain. To enable successful delivery of the project there will be a need for activities which may include stakeholder/public engagement, consent applications, land access/acquisition, surveys and mitigation. There is potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals. 1 (LOW) = PLE issues identified but which can be managed through specialist resource and BAU processes within proposed output date. Some limited potential for conflict with environmental, third party and/or customer constraints. Applicable agreements, permissions or regulatory consents are likely to be necessary but straightforward. There is low potential for negative reputational impact and customer complaints associated to 3rd Party and/or environmental aspects of the proposals.

## Identify
Constraints Checklist - Section 2
Ref | Category | Affected/ Required? Yes/No/Potentially | Details | Reference
1 | Designations | Yes | Planning Policy Designation: Netherley [✂] and Greensbridge [✂] are located within an area of designated Greenbelt . | Refer to Constraints tab and Environmental Review Plan
3 | Trees & Hedgerows | Yes | Trees are located at all three sites. These are of particular importance at Netherley and Greensbridge [✂] due to the Greenbelt designation. There are a group of TPO trees adjacent to Netherley [✂] site boundary which should be avoided. There will be a need for a tree survey and an assessment of effects/impacts including proposed retention, protection and mitigation of effects on trees.
4 | Amenity Landscapes (e.g. Sports Pitches, Greenspace, Green-infrastructure) | Yes | The proposed area for development adjacent to Netherley [✂] is an open area of amenity greenspace located within a residential area and adjacent to a Sports Club. Early engagement required to determine the solution.
5 | Access land - Village Green, Common Land, Millennium Greens etc. | No
6 | Heritage and Archaeology | No
| Tree Preservation Order | Yes | There are a group of TPO trees adjacent to Netherley [✂] site boundary which should be avoided.
7 | Public Right of Way | No
8 | Main Rivers | Yes | Greensbridge and Netherley [✂] are loacted in close proximity to main rivers. A Flood Risk Activity Permit will be required from the Environment Agency for any works within 8m unless exempt. A Flood Risk Assessment and Geomorphological Assessment will be required to support the applications. Early consultation with the Environment Agency will be required.
9 | Ordinary Watercourses | No
| Flood Risk Zone | Yes | Greensbirdge [✂] is located within Flood Risk Zone 2 and 3. Any works outside of Flood Zone 1 a will require a Flood Risk Assessment to accompany the Planning Application. Early engagement needed with the EA
16 | EIA Screening Opinion | Potentially | An EIA Screening Opinion will be required for any new or extended [✂] facilities.
17 | Environmental Impact Assessment | Potentially | The outcome of the Screening Opinion will determine if an EIA is required to support the planning application. If one if required this will add signficant time and cost onto the programme.
18 | Planning Permission | Yes | Planning permission would be required for the proposed extension at Netherley onto third party land, Any large buildings including kiosks on UU operational land at Belle Vale and Greensbridge would require permission and any new accesses off a classifed road. In the event that an EIA is required all Permitted Development Rights would be withdrawn and Planning Permission would be required for the overall scheme.
29 | Discharge Permit | Yes | Any new discharge permits should be confirmed with the Environment Agency. For any amendments to an existing discharge consent then the PEM / PMC should discuss this with the UU Environmental Regulation Team
30 | Abstraction Licence | No
Yes
No
Potentially
Note on A2: Rimmer, Tom: • If any aspect is affected/potentially affected set this out in this section and provide brief details of the constraint/requirement and any reference for future Information for Tenderers (IfT). • If unaffected click “no” and this aspect will not appear in the next tab…
Note on D5: Watson, Dave (Planning): what do the brown dots mean on the local plan at netherley?

## Timeline
Third Party, Environment and Customer Action Plan - Section 3 - Timeline
The specific timeline for the Project will be developed in collabrative planning sessions. The typical windows and timescales for key Third Party and PLE Activities are summarised below
PLEASE NOTE TIMESCALES BELOW ARE BASED ON TYPICAL TIMESCALES AND STATUATORY DETERMINATION PERIODS AND THE TIMESCALES FOR APPROVAL ON PROJECTS COULD BE SIGNIFICANTLY LONGER AND SHOULD BE SET OUT IN COLLABRATIVE PLANNING SESSIONS
Application Type | Restrictions | External Cost | Timescale (Weeks)
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Abstraction | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
Impoundment | If Pre App Required assume 8 months required for this | Yes | Timescale (Weeks) 1: Currently 6 months till scheme allocated to a case officer - this is subject to change | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE
EIA Screening (LPA) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
EIA Screening (Marine) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Marine Licence |  | Yes | [52 empty] | PLEASE NOTE THAT THESE TIMESCALES ARE THE STATUATORY ONES HOWEVER NORMALLY HAVE SIGNIFICANLY LONGER PERIODS TO DETERMINE | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 20
Footpath Diversions (Temp) |  | Yes | Timescale (Weeks) 1: Between 6 and 14 weeks depending on the council
Footpath Diversions (Perm) |  | Yes
Tree Works (TPO or Conservation Area) |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Hedgerow Removal Notice |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Planning (Water) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Planning (Waste) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 15
Planning (EIA) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 18
Planning (Condition Discharge) |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Scheduled Monument Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Listed Building Consent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Reg 76 / 77 Application |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 3
EA Flood Risk Activity Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Lead Local Flood Authority Consent |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 8
S278 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 14
S184 | Can only be applied for once Planning Permission Granted | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 9
Habitat Regulations Assessment |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
SSSI Assent |  | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Protected Species Licence | Can only be applied for once Planning Permission Granted | No | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4
Industrial Emmisions Permit |  | Yes | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 12
Hazardous Substances Consent | bar: Timescale (Weeks) 1 to Timescale (Weeks) 4; Timescale (Weeks) 7 to Timescale (Weeks) 10
Approximate period for application to be allocated to case officer
Typical duration for registration of application once allocated to case officer
Statuatory determination period

## Environmental Review Plans
[✂]